## Abstract
EARNED VALUE ANALYSIS
Month | M-6
| Planned Value | 97.79 | Earned Value | 66.0083 | Actual Cost | 78
| 8 |  |  | 6 |  | 10
Parameter |  | Value |  | Implications
Cost Varriance |  | -11.9917 |  | Over Budget
Cost Performance Index |  | 0.84626 |  | Over Budget
Schedule Varriance |  | -31.7817 |  | Behind Schedule
Schedule Varriance Index |  | 0.675 |  | Behind Schedule

## Datasheet
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Timeline | Planned-Progress | PV | Actual-Progress | AC | EV-Cumm | Planned-Cumm Progress | Cumm-PV | Actual-Cumm Progress | AC-Cumm
M-1 | 1.389% | 12.2237 | 0.5% | 10 | 4.4005 | 1.389% | 12.2237 | 0.5% | 10
M-2 | 1.389% | 12.2237 | 0.5% | 8 | 8.8011 | 2.778% | 24.4475 | 1% | 18
M-3 | 1.389% | 12.2237 | 1% | 10 | 17.6022 | 4.167% | 36.6713 | 2% | 28
M-4 | 1.389% | 12.2237 | 2% | 5 | 35.2044 | 5.556% | 48.895 | 4% | 33
M-5 | 2.778% | 24.4475 | 3% | 20 | 61.6077 | 8.333% | 73.3425 | 7% | 53
M-6 | 2.778% | 24.4475 | 0.5% | 25 | 66.0083 | 11.11% | 97.79 | 7.5% | 78
M-7 | 2.778% | 24.4475 | 2% | 30 | 83.6105 | 13.89% | 122.2375 | 9.5% | 108
M-8 | 4.167% | 36.6713 | 3% | 40 | 110.0138 | 18.06% | 158.9087 | 12.5% | 148
M-9 | 4.167% | 36.6713 | 5% | 50 | 154.0192 | 22.22% | 195.58 | 17.5% | 198
M-10 | 4.167% | 36.6713 |  |  | #N/A | 26.39% | 232.2512 | #N/A
M-11 | 5.556% | 48.895 |  |  | #N/A | 31.94% | 281.1462 | #N/A
M-12 | 6.944% | 61.1188 |  |  | #N/A | 38.89% | 342.265 | #N/A
M-13 | 6.944% | 61.1188 |  |  | #N/A | 45.83% | 403.3837 | #N/A
M-14 | 6.944% | 61.1188 |  |  | #N/A | 52.78% | 464.5025 | #N/A
M-15 | 6.944% | 61.1188 |  |  | #N/A | 59.72% | 525.6212 | #N/A
M-16 | 6.944% | 61.1188 |  |  | #N/A | 66.67% | 586.74 | #N/A
M-17 | 8.333% | 73.3425 |  |  | #N/A | 75% | 660.0825 | #N/A
M-18 | 5.556% | 48.895 |  |  | #N/A | 80.56% | 708.9775 | #N/A
M-19 | 4.167% | 36.6713 |  |  | #N/A | 84.72% | 745.6487 | #N/A
M-20 | 4.167% | 36.6713 |  |  | #N/A | 88.89% | 782.32 | #N/A
M-21 | 2.778% | 24.4475 |  |  | #N/A | 91.67% | 806.7675 | #N/A
M-22 | 2.778% | 24.4475 |  |  | #N/A | 94.44% | 831.215 | #N/A
M-23 | 2.778% | 24.4475 |  |  | #N/A | 97.22% | 855.6625 | #N/A
M-24 | 2.778% | 24.4475 |  |  | #N/A | 100% | 880.11 | #N/A
| 100% | 880.11 |  |  | #N/A | 100% | 880.11 | #N/A | 198
Input Tables